CS 192 Software Engineering II
Implementation Plan and Accountability Report

Developer’s Group Name: johnjudeandjennie
Project Name: SARAPP sa UP

In this sheet, record planned activities for the sprint. This should be updated per sprint and submitted to the instructor.
Sprint No.	Date	Activity	Accountability / (Name of Person)	Output	Done / (Y/N)	Remarks
1	Jan 25-27	Plan and prepare Sprint Review Checklist.	Jennie Ron Ablog	Implementation Plan	Y
	Jan 25-30	Code basic website with feature/s (input store). Probably include Add Store feature.	John Christian Sun	SARAPP-sa-UP.zip	Y
	Jan 30	Test input store feature. Probably test Add Store feature too.	Jennie Ron Ablog		Y
	Jan 31	Review the code.	Jennie Ron Ablog	Code Review Result
	Feb 3	Sprint Review	John Christian Sun	Sprint Review Document	Y
	Feb 3	Sprint Retrospect	John Christian Sun	Sprint Retrospect Document	Y	Link to Sprint Release Codes in GitHub
2	Feb 5	Plan and prepare Sprint Review Checklist	John Christian Sun	Implementation Plan	Y
	Feb 7-13	Code store searching feature. Improve interface if needed.	Jennie Ron Ablog	SARAPP-sa-UP Sprint 2.zip	Y

	Feb 13	Test store searching feature.	John Christian Sun	Test Scorecard Result	Y
	Feb 13	Review code for store searching feature	John Christian Sun	Code Review Result
	Feb 17	Sprint Review	Jennie Ablog	Sprint Review Document
	Feb 17	Sprint Retrospect	Jennie Ron Ablog	Sprint Retrospect Document	Y

Sprint No.	Date	Activity	Accountability / (Name of Person)	Output	Done / (Y/N)	Remarks
3	Feb 17	Plan and prepare Sprint Review Checklist.	Jennie Ron Ablog	Implementation Plan	Y
	Feb 18-28	Add input location feature.	John Christian Sun	SARAPP-sa-UP Sprint 3.zip	Y
	Mar 1	Test input location feature.	Jennie Ron Ablog		Y
	Mar 2	Review the code.	Jennie Ron Ablog	Code Review Result
	Mar 3	Sprint Review	John Christian Sun	Sprint Review Document
	Mar 3	Sprint Retrospect	John Christian Sun	Sprint Retrospect Document	Y	Link to Sprint Release Codes in GitHub
4	Mar 3	Plan and prepare Sprint Review Checklist	John Christian Sun	Implementation Plan	Y
	Mar 4 – 15	Code rating store functions	Jennie Ron Ablog	SARAPP-sa-UP Sprint 4.zip
	Mar 4 – 15	Fix UI of existing functions	John Christian Sun
	Mar 15	Test store searching feature.	John Christian Sun	Test Scorecard Result
	Mar 15	Review code for store searching feature	John Christian Sun	Code Review Result
	Mar 17	Sprint Review	Jennie Ablog	Sprint Review Document
	Mar 17	Sprint Retrospect	Jennie Ron Ablog	Sprint Retrospect Document